

**RIMARY CARE JOINT COMMISSIONING COMMITTEE**

**Part 1**

ACTION LIST June 2021

| **MEETING DATE / MINUTE NO.** | **SUBJECT / ACTION REQUIRED** | | **ACTION REQUIRED BY** | **TIMESCALE** | | **STATUS OF ACTION**  **R.A.G.** |
| --- | --- | --- | --- | --- | --- | --- |
| **23.10.20 8.5** | **Primary Care Covid-19 Response Engagement Update Report** | | | | | |
| The Final Primary Care COVID – 19 Response to be brought to a future Committee.  **Status Update** – an update was provided in Part 2 of a January 2021 Extraordinary Primary Care Commissioning Committee, and it was agreed amendments would be undertaken and a revised paper be brough to the April 2021 Committee  **Status Update 26.02.21 -**  **Status Update 23.04.21** - An interim high-level report would be brought to the August 2021 Primary Care Commissioning Committee. The delay in bringing the paper back was due to the pre-election period and the Communications and Engagement Team not being able to commence any work until after the 7th May 2021.  **Status Update 25.06.21 -** There would be an interim headline report completed for October 2021 Committee. The original delay was due to the local elections and guidance not to commence any engagement work in the pre-election period. | Head of Engagement | | Amended to October 2021 | **In Progress** | |
| Further information on how non-English speaking patients’ appointments were handled was requested | Head of Engagement | | December 2021 |  | |

| **MEETING DATE / MINUTE NO.** | **SUBJECT / ACTION REQUIRED** | | **ACTION REQUIRED BY** | **TIMESCALE** | | **STATUS OF ACTION**  **R.A.G.** |
| --- | --- | --- | --- | --- | --- | --- |
| **23.04.21**  **8.5** | **Repeat Contraception – Sexual Health Services** |  | |  |  | |
| It was requested the repeat contraception service be closely monitored for six months and an outcome report be brought to the February 2022 Committee. | Commissioning Lead - Quality | | February 2022 |  | |

Key:

|  |  |
| --- | --- |
| **Completed / Closed** |  |
| **In Progress** |  |
| **To Action** |  |
| **To be Actioned but date not yet due** |  |